# MONITORING AND CONTROL PLAN

This framework helps in tracking, evaluating and controlling the quality and progress of the Smart Modular Indoor Farming pods project. This plan aims to ensure that the project is delivered on time within the specified budget alongside meeting the performance, quality and user satisfactions as main objectives. Active oversighting will enable the early detection of any deviations and prompt corrective actions, maximizing the success of project.

ROLES AND RESPONSIBILITIES:

- PROJECT MANAGER: Maintains the up-to-date action plans, consolidates the project status reports of project, monitors the milestone and escalates the issues/risks related to project.

- HARDWARE LEAD: Monitors the development and testing of the sensors, home pod designs, and electronic integration in pods.

- SOFTWARE LEAD:  Tracks the app development, integration testing and user feedback analysis to update the app interface and features.

- QA LEAD: Ensures adherence to the functional and usability criteria, conducts the testing of products and documents the results of each test.

- FINANCE LEAD: Overseas the budget tracking and cost reporting of the project.

MONITORING TOOLS:

- PM Tools: MS Project ad Trello for the task assignment, progress tracking of project at each phase, and Gantt chart visualization.

- Documentation Repositories: OneDrive/Google drive/Confluence for the centralized project documentation and data logging.

- Spreadsheet based repository documenting the risks/issues and their status along with the mitigation plans for each of them.

ACTIVITIES:

| REPORT | DUE ON | RESPONSIBLE | DESCRIPTION |
| --- | --- | --- | --- |
| Progress Report 1 | Post completing the initial research and planning phase | Project Manager / Hardware manager | Gives overview of the completion of the phase and early findings of the project |
| Progress Report 2 | Post completing prototype design and app development | Software Lead / QA Lead | Provides information on prototype integration and app functionality |
| Progress Report 3 | Post completing the initial testing and risk mitigation | QA Lead / Finance Lead | Gives test results summary, budget updates and risk reviews |
| Interim Report | During the midpoint of project | Project Manager | Provides comprehensive status update of project along with critical analysis |
| Progress Report 4 | Post completing pilot testing and collecting user feedback | Software Lead / QA Lead | App/Pod performance review and user feedback |
| Final Report | Project Completion | Project Manager | Final assessment of project along with lessons learned during project phase and future recommendations |

REPORT SCHEDULE (ACCORDING TO WBS)

Progress Report 1 – After completion of Initiation Phase (A1-A4) – Week 2

- A1: Conduct Feasibility Study

- A2: Identify Key Stakeholders

- A3: Develop Project Charter

- A4: Finalize Project Charter

Progress Report 2 – After completion of Planning Phase (B1-B4) – Week 4

- B1: Define Project Scope

- B2: Identify Resources & Team

- B3: Develop Work Schedule

- B4: Budget Estimation

Progress Report 3 – After completion of Design Activities (C1-C2) – Week 7

- C1: Design Indoor Farming Pod

- C2: Procure Materials and Components

Progress Report 4 – After completion of Assembly & Testing (C3-C4) – Week 9

- C3: Assemble Pod Prototype

- C4: Testing of LED Systems

Interim Report – Mid-project Review – Week 6

Progress Report 5 – After completion of Control Phase (D1-D4) – Week 10

- D1: Project Monitoring & Evaluation

- D2: Risk Assessment

- D3: Quality Control Review

- D4: Performance Reports

Progress Report 6 – After completion of Marketing Activities (E1-E4) – Week 11

- E1: Develop Marketing Strategy

- E2: Create Branding & Packaging

- E3: Conduct Market Research

- E4: Determine Pricing

Final Report – End of Week 12 – Final prototype demonstration and project closeout

To ensure effective monitoring, a strong control system will be established. The system will be flexible, cost-effective, and designed to meet the real operational needs of the project. The following documentation will be required for effective Performance Control:

- Maintenance logs for pods and sensor systems

- Quality control checklists (environmental control, structural stability)

- Test results of automation, irrigation, and energy systems

- Engineering Change Orders related to pod structure, IoT systems, or materials

PERFORMANCE MEASUREMENT:

KPIs:

  - SCHEDULE ADHERENCE: Adherence to the completion of each phase within a (+/-) 5% tolerance to the timeline.

  - PROTOTYPE FUNCTIONALITY:

    - Sensor data accuracy > 95%

    - App command success rate > 95%

  - Plant Growth Success: More than 4-5 plants should sustain in the pod design during the pilot testing of pods.

  - User Satisfaction: >80% of positive feedback from users/customers post launching the pilot pod to the participants/customers.

  - Budget Compliance: Maintain the expenses within (+/-) 10% of the allocated budget for each phase/project.

  - Risk Responsive Effectiveness: Resolving/mitigating the risks identified within the designated timelines.

Earned Value Management:

Critical ratio is used to quantify the performance for comparing the actual progress against the planned values.

Critical Ratio (CR) = [(Actual Budget)/ (Budgeted Progress)] *[(Budgeted cost of work)/ (Actual Cost of work)] NOTE:

CR > 1, indicates over performance

CR<1, indicated the under performance

Tolerance threshold for CR deviation is (+/-) 5%

# FINANCIAL PLAN

The following plan outlines the estimated expenses for the Smart Modular Indoor Farming Pods Project. The financial estimates are based on the resources required for the 12-week development cycle, including hardware, sensors, software tools, prototype fabrication, and personnel time.

## Assumptions:

- No overhead costs such as rent, utilities, or administrative fees are included.

- Personnel expenses are represented as estimated labor value for engineering and design work, not full-time salaries.

- Lab access, 3D printing tools, and basic fabrication equipment are assumed to be provided by the institution.

- Personnel are compensated on a monthly basis.

- Hardware costs reflect prototype-level quantities, not bulk manufacturing.

## Budgeting Method:

The total budget ceiling for the project was determined first, which was originally estimated to be $185–$455 for hardware, sensors, and software tools. After this determination, the funding was allocated across project phases and functional departments. This method is beneficial given the project's short duration and the need for rapid procurement and coordination amongst teams. This approach helps ensure resources remain aligned with the project's critical success factors, facilitates rapid decision-making, minimizes planning time, and supports efficient task allocation.

## Table 1: Materials and Cost

| Task/Material | Estimated Cost, USD |
| --- | --- |
| Microcontroller board [Arduino/ESP32] | $30 |
| Humidity, temperature, and water sensors | $40 |
| LED grow light strips | $45 |
| Pod structural materials [acrylic, PVC, modular joints] | $60 |
| Wiring, power adapters, fasteners | $25 |
| Prototype fabrication supplies | $30 |
| App mockup software [Adobe] | $20 |
| CAD design tool access | $15 |
| Project management platform [Trello premium, MS project] | $20 |
| Contingency [10-15%] | $25 |
| Total Cost | $310 |

## Table 2: Estimated Personnel Cost

| Role | Approx. Hours | Rate per Hour | Total Estimated Cost |
| --- | --- | --- | --- |
| Lead Hardware Engineer / Electrical Engineer | 25 | $20 | $500 |
| Electrical Engineer | 20 | $18 | $360 |
| Mechanical Engineer | 20 | $18 | $360 |
| Systems Integration Engineer | 15 | $20 | $300 |
| Prototype Manufacturing Engineer | 15 | $18 | $270 |
| Software Engineer | 25 | $20 | $500 |
| App Developer | 20 | $20 | $400 |
| Data Analyst | 10 | $18 | $180 |
| Agricultural Specialist | 15 | $18 | $270 |
| Environmental Engineer | 10 | $18 | $180 |
| UX/UI Researcher | 10 | $18 | $180 |
| Quality Engineer | 10 | $18 | $180 |
| Risk Analyst | 10 | $18 | $180 |
| Procurement Specialist | 8 | $18 | $144 |
| Pilot Test Coordinator | 8 | $18 | $144 |
| Field Technician | 10 | $18 | $180 |
| Operations Manager | 8 | $20 | $160 |
| Total Estimated Personnel Effort Cost |  |  | $4,338 |

## Total Estimated Project Cost:

Material and Tools: $310

Personnel Effort Value: ~$4,338

Overall Total Estimated Cost: ~$4,648

## Estimated Budget Summary

Based on our earlier HWs and updated vendor checks, the expected budget for building functional prototypes and completing app mockups ranges from:

$260 – $520

This represents the direct material and incremental costs for prototype development. The personnel costs listed in Table 2 reflect estimated labor value rather than cash outlay, as team members are contributing time as part of academic project requirements.

Cost Breakdown by Category

### i. Electronics & Sensors ($90 – $180)

- Microcontroller (ESP32 or Arduino): $12 – $25

- Humidity, temperature, and soil moisture sensors (3-5 units): $30 – $60

- Light sensors: $10 – $20

- Water-level or capacitive sensors: $15 – $25

- IoT/wireless module backups: $20 – $50

### ii. Lighting & Power ($20 – $40)

- Energy-efficient LED grow lighting (under 15W): $15 – $25

- Power adapters, wiring, connectors: $5 – $15

### iii. Prototype Pod Materials ($70 – $140)

- PLA/ABS filament for 3D printing: $20 – $35

- Acrylic sheets or modular frame supports: $30 – $60

- Hardware (screws, mounts, brackets): $10 – $20

- Testing pots/soil/nutrients for plant trials: $10 – $25

### iv. Software & App Development ($10 – $50)

- App mockup tools (Figma, Adobe alternatives – free to low-cost student plans): $0 – $20

- Cloud storage for IoT data trials (low-tier): $0 – $10

- Misc. software tools / integrations: $10 – $20

### v. Project Management, Contingencies & Reporting ($50 – $110)

- Contingency for part failures or redesigns: $30 – $70

- Printouts, presentation materials, binders, markers: $10 – $20

- Miscellaneous testing supplies: $10 – $20

## Financial Monitoring Approach

### i. Weekly Budget Tracking

A shared Google Sheet records:

- Planned cost

- Actual cost

- Variance

- Notes for over- or under-spend

Any line item exceeding its allocation by more than 15% is reviewed by the team during weekly meetings.

### ii. Cost-Control Measures

- Prioritize low-cost, beginner-friendly sensors (DHT22, BH1750, capacitive moisture sensors).

- Use university resources (3D printers, lab materials) whenever allowed.

- Limit redesign cycles by validating CAD files before printing.

- Reuse soil, trays, and pots during plant trials.

- Only upgrade components if absolutely required for the proof of concept.

### iii. Procurement Strategy

- Order critical sensors from two vendors to avoid delays.

- Purchase all non-electronic materials at once to reduce shipping costs.

- Keep receipts and track all expenses for transparency.

## Financial Risk Evaluation

High-risk areas:

- Prototype redesign costs due to misalignment

- Sensor or module replacement due to failure

- Additional lighting costs if early growth trials underperform

Mitigation:

- Allocate the highest contingency buffer to hardware

- Run early small-scale tests to confirm environmental stability

- Avoid non-essential custom components during early weeks

## Expected Cost at Completion (EAC)

Given current assumptions and past HW risk analysis:

Projected Final Spend: $290 – $450

(Well within the $260–$520 allocated budget range)

This includes hardware, materials, app prototyping, plant trial consumables, and all final report/presentation materials.

## Cost-Benefit Analysis

This project is a prototype development effort, not full commercial manufacturing, so the cost-benefit analysis focuses on conceptual market feasibility.

Assumptions for Economic Evaluation:

- Estimated retail price per pod (P): $120–$150.

- Per-unit manufacturing cost (VC): $35–$45.

- Estimated early-adopter interest in the Boston urban market: moderate (n=15-20 beta users).

### 1. Break-Even Analysis:

The break-even quantity is calculated using the formula:

Break-even quantity = FC / (P - VC)

Where:

- FC = fixed development cost (project cost) = $4,648

- P = retail price (used for calculation) = $135

- VC = manufacturing cost (used for calculation) = $40

- P - VC = Margin = $95

The break-even units calculation is: $4,648 / $95 = 49 pods

### 2. Prototype ROI:

The Return on Investment (ROI) formula is:

ROI = (Net profit After Break-even / Initial Investment) × 100

- Revenue (at break-even): 49 × $135 = $6,615

- Manufacturing Cost (at break-even): 49 × $40 = $1,960

- Net profit After Break-even: $6,615 - $1,960 - $4,648 = $7

- Initial Investment: $4,648

ROI = ($7 / $4,648) × 100 ≈ 0.15%

### Conclusion

With a retail price of $135 per pod and a manufacturing cost of $40, the project reaches break-even at 49 pods. At this point, the net profit is only $7, resulting in an ROI of approximately 0.15%, which means the initial investment of $4,648 is fully recovered. Sales beyond 49 pods will generate positive returns. While the project is primarily a 12-week development and research effort, this analysis demonstrates that the project is cost-effective and manageable within the allocated budget.

## Summary

In this financial plan I've covered all estimated expenses, cost assumptions, budgeting practices, and cost-control strategies needed to complete the 12-week prototype and launch preparation. The budget reflects realistic market rates for student engineering labor and component costs, while leveraging institutional resources to minimize overhead expenses. With proper tracking and adherence to cost-control measures, we expect to deliver a functional prototype within our allocated budget. The cost-benefit analysis further validates the commercial viability of the project, demonstrating that break-even can be achieved with modest market penetration